Part 1 — Complete Answer Key for Crisis Cabinet

Here are all 36 correct answers (3 decisions × 12 scenarios):

S1 — Key Developer Departure (Planning)

- Classify: 🐯 Tiger (Confirmed departure = High Prob × undocumented schema = High Impact)

- Strategy: B — Mitigate (Require 4 KT sessions + full schema documentation before last day)

- Mitigation: A (Run 4 knowledge-transfer sessions AND create schema map with entity relationships, constraints, and stored procedures before developer leaves)

S2 — Regulatory Framework Change (Planning)

- Classify: 🐊 Alligator (30% probability = Low × full architecture rebuild = High Impact)

- Strategy: B — Transfer (Contract clause: regulatory re-architecture billed as separate change request)

- Mitigation: A (Draft contract clause specifying regulatory-change-driven re-architecture is billed as a separate change request, with a pre-agreed rate card)

S3 — Scope Creep Requests (Planning)

- Classify: 🐶 Puppy (High probability — almost certain in any stakeholder-facing project × Low individual impact)

- Strategy: B — Mitigate (Formal CCB; each request requires written impact assessment before approval)

- Mitigation: A (Establish a Change Control Board meeting bi-weekly; each request requires a written impact form — effort, cost, timeline effect — before vote)

S4 — Payment Gateway Offline (Executing)

- Classify: 🐯 Tiger (Risk has materialised = Probability 1.0 × 100% of transactions blocked = Critical Impact)

- Strategy: B — Mitigate (Activate pre-built secondary gateway with automated failover)

- Mitigation: A (A pre-integrated secondary payment gateway — e.g. Stripe — with automated failover, tested in staging, activatable in under 15 minutes)

S5 — Standup Overruns (Executing)

- Classify: 🐶 Puppy (High probability — happens every day × Low impact per meeting, but compounding)

- Strategy: B — Mitigate (Strict 15-minute timebox + parking lot calls with only relevant people)

- Mitigation: A (Introduce a physical/virtual timer visible to all; any problem-solving after the 15-min mark moves to an immediate follow-up call with only affected team members)

S6 — Zero-Day CVE (Executing)

- Classify: 🐊 Alligator (No active exploits = Low Prob × full user data breach = Catastrophic Impact)

- Strategy: B — Mitigate (Emergency hotfix sprint + automated dependency scanning in CI/CD)

- Mitigation: A (Deploy emergency hotfix patching the library within 24 hours; enable a WAF rule blocking exploit patterns as an interim shield; add CVE monitoring to CI pipeline)

S7 — Budget Overrun CPI 0.77 (Monitoring)

- Classify: 🐯 Tiger (CPI 0.77 = actively happening = High Prob × €42k in a fixed-price contract = High Impact)

- Strategy: B — Mitigate (Immediate cost-reduction: right-size cloud, defer non-essential features)

- Mitigation: A (Audit all cloud resource usage in the next 48 hours; right-size over-provisioned instances; identify 2–3 lowest-priority features to defer to a post-launch phase)

S8 — PDF Table Border 1px Off (Monitoring)

- Classify: 🐱 Kitten (2% occurrence = Low Prob × cosmetic only, data correct = Negligible Impact)

- Strategy: D — Accept (Log in known issues register, note in export help text, review in 3 months)

- Mitigation: A (Add to the known issues backlog with low priority; add a tooltip in the export dialog noting the Windows/Adobe Reader edge case; review at next quarterly planning)

⚠️ The trap here: Most students pick Mitigate. The correct answer is Accept — burning sprint capacity on a 2% cosmetic issue is the anti-pattern being tested.

S9 — Single-AZ Cloud Failure (Monitoring)

- Classify: 🐊 Alligator (<0.3% AZ outage = Very Low Prob × 15 hospitals + patient care = Severe Impact)

- Strategy: B — Mitigate (Multi-AZ deployment with active-active load balancing and automated failover)

- Mitigation: A (Implement multi-AZ deployment with active-active load balancing; configure health checks and automatic failover with RTO < 60 seconds; test failover quarterly)

S10 — UAT Sign-off Blocked (Closing)

- Classify: 🐶 Puppy (High probability — same pattern on last 3 milestones × Low-Medium impact, days not project failure)

- Strategy: B — Mitigate (Escalate to line managers + hard 48-hour deadline + one-click approval form)

- Mitigation: A (Provide a single-page visual summary of changes requiring sign-off; set a 48-hour deadline with explicit impact on go-live; CC the project sponsor on the request)

S11 — API 8–12s at Load Test (Closing)

- Classify: 🐯 Tiger (Confirmed by testing = Probability 1.0 × delivery rejection + payment withheld = High Impact)

- Strategy: B — Mitigate (Senior engineers exclusively on DB optimisation: query restructuring, index creation, caching)

- Mitigation: A (Run performance profiling to identify top 5 slow queries; add missing composite indexes; implement Redis caching for frequently-accessed read endpoints; retest under load within 48 hours)

S12 — Broken Documentation Link (Closing)

- Classify: 🐱 Kitten (Single confirmed link, documentation-only = Low Prob × negligible, feature works = Negligible Impact)

- Strategy: B — Mitigate (Fix it immediately — 15 minutes in a 9-day window is proportionate)

- Mitigation: A (Fix the broken link right now (15 minutes); run a link-checking tool across all documentation pages to catch any other broken links before launch)

⚠️ The second trap: Unlike S8 (Accept), S12 is Mitigate — because the fix takes 15 minutes and you have 9 days. Kitten does not automatically mean Accept; it means proportionate response